## Cap_Prog_2017-18
Capital Programme 2017/18 to 2020/21
Scheme details |  | Approval | Approved | Actual | Revised | Revised | Revised | Revised | Aniticipated | Change | Comments | Approved | Revised |  | Actual | Probable | Variance | Comments
|  | Date | Budget | 31 Mar 17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | Outturn |  |  | Budget | Budget |  | Apr - Jan | 2016/17
|  |  | £ | £ | £ | £ | £ | £ | £ | £ |  |  |  |  | £ | £
Housing Services | [11 empty] | 0
Improvement Grants/Loans (private sector properties) | [11 empty] | 0
| Disabled Facilities Grants | CMC - Jan 2015 | 2095000 |  | 505000 | 520000 | 535000 | 535000 | 2095000 | 0 |  | 2402040 | 2095000 | 307040 | 62949 | 307040 | -244091
| Discretionary Renovation Grants | CMC - Jan 2015 | 117310 |  | 28255 | 29103 | 29976 | 29976 | 117310 | 0 |  | 144742 | 117310 | 27432 |  | 27432 | -27432
| Minor Works Assistance Grants | CMC - Jan 2015 | 66410 |  | 15995 | 16475 | 16970 | 16970 | 66410 | 0 | Subject to future Cttee report | 81938 | 66410 | 15528 | 2256 | 15528 | -13272
| Loans - Granted | CMC - Jan 2015 | 160000 |  | 40000 | 40000 | 40000 | 40000 | 160000 | 0 |  | 200000 | 160000 | 40000 |  | 40000 | -40000
| Moving Home Scheme Loans | CMC - Jan 2015 | 115687 |  | 27865 | 28700 | 29561 | 29561 | 115687 | 0 |  | 142741 | 115687 | 27054 |  | 27054 | -27054
Capital Schemes (non-council housing) | [8 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0
| New Housing Schemes - Grants to partner organisations | CMC - June 2014 | 1200000 |  | 300000 | 300000 | 300000 | 300000 | 1200000 | 0 |  | 1500000 | 1200000 | 300000 | 7540 | 300000 | -292460
Capital Schemes (HRA Housing) | [8 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0
| Purchase of Property | Hsg - Sept 2016 | 5200000 |  | 1300000 | 1300000 | 1300000 | 1300000 | 5200000 | 0 | Part financed by use of Housing receipts not paid to the Government Pool | 6100000 | 5200000 | 900000 | 289816 | 900000 | -610184
| Ilex and Cherrywood New Houses | CMC - Mar 2017 | 2285492 | 90809 | 1475184 | 719499 |  |  | 2285492 | 0 |  | 2292000 | 2285492 | 6508 | 39385 | 200000 | -160615
| Reprovision of flood damaged houses (Farm Close) | Hsg - Sept 2016 | 822000 | 12004 | 430000 | 380000 |  |  | 822004 | 4 |  | 822000 | 822000 | 0 | 4365 | 50000 | -45635
| New Potential Build Schemes, Egham | - | 6370000 |  | 1010000 | 2000000 |  |  | 3010000 | -3360000 | Subject to future Cttee report | 6370000 | 6370000 | 0
| St Georges Development, Addlestone | - | 0 |  | 860000 | 1740000 |  |  | 2600000 | 2600000 | Subject to future Cttee report |  | 0
| Replacement of Estate Vehiicle | CMC - Mar 2017 | 10600 |  | 10600 |  |  |  | 10600 | 0 |  |  |  | 0
0
|  | Sub-totals | 18442499 | 102813 | 6002899 | 7073777 | 2251507 | 2251507 | 17682503 | -759996 |  |  |  | 0 | 406311 | 1867054
Environment & Sustainability | [8 empty] | 0 | 0 |  |  |  | 0
Environmental Services | [8 empty] | 0 | 0 |  |  |  | 0
| Vehicle fleet replacement programme: |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0
| - Approved provision | CMC - Mar 2017 | 334120 |  | 334120 |  |  |  | 334120 | 0
| - Future provision | - | 925000 |  | 25000 | 300000 | 300000 | 300000 | 925000 | 0 | Requires Cttee approval to spend | 1214661 | 925000 | 289661 | 263056 | #NAME? | #NAME?
| - In-cab technology/Bartec | CMC - Jul 2016 | 37500 |  | 37500 |  |  |  | 37500 | 0 | Subject to future Cttee report
| Runnymede Roundabout | CMC - Oct 2014 | 500000 | 250000 | 250000 |  |  |  | 500000 | 0 | £250,000 Funded from S106 monies | 500000 | 500000 | 0 |  | 500000 | -500000
| VW car park reprovision | CMC - Aug 2016 | 50000 | 44665.02 | 5335 |  |  |  | 50000.02 | 0.02 |  | 50000 | 50000 | 0 | 44537 | 50000 | -5463
| Memorial Gardens Car Park VW | CMC - Feb 2017 | 300000 |  | 300000 |  |  |  | 300000 | 0 | Additonal £75,000 approved CMC June 2017
|  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0
|  | Sub-totals | 2146620 | 294665.02 | 951955 | 300000 | 300000 | 300000 | 2146620.02 | 0.02 |  |  |  | 0 | 307593 | #NAME?
Community Development |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0
Community Transport |  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0
| Vehicle fleet replacement programme: |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0
| - Citreon relay 1.4 H2 minibus (Patient Transport Contract) | CMC - Sept 2016 | 40000 |  | 37854 |  |  |  | 37854 | -2146
| - Replacement vehicle | CMC - Jun 2016 | 40000 |  | 40000
| - Relpacement Vehicle - Ashford Hub | CMC - Jun 2016 | 45000 |  | 45000
| - Future provision | - | 145146 |  | 52146 | 45000 | 48000 |  | 145146 | 0 | Requires Cttee approval to spend | 138000 | 145146 | -7146
Safer Runnymede |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0
| CCTV Equipment Replacement | - | 537001 |  | 132001 | 135000 | 135000 | 135000 | 537001 | 0 | Annual provision available to draw down | 596484 | 537001 | 59483 | 48035 | 73984 | -25949
Grant Aid to Sporting and Community Organisations | [8 empty] | 0 | 0 |  | 0 | 0 | 0
| Grants to Local Organisations | - | 88000 |  | 28000 | 20000 | 20000 | 20000 | 88000 | 0 | Annual provision available to draw down | 120000 | 88000 | 32000 | 22320 | 38000 | -15680
Parks and Open Spaces | [8 empty] | 0 | 0 |  | 0 | 0 | 0
| Marshall Place Open Space, New Haw | CMC - Sept 2014 | 90500 | 11189 | 79311 |  |  |  | 90500 | 0 | Project Completion programmed for summer 2017 | 90500 | 90500 | 0 | 2004 | 79311 | -77307
| Fernlands Open Space | CMC - Sept 2011 | 101000 | 27906 | 73094 |  |  |  | 101000 | 0 | Funded by S106/Planning Tariff monies | 101000 | 101000 | 0 | 2881 | 73094 | -70213
| Kings Lane Open Space play area | CS - Jan 2017 | 28000 |  | 28000 |  |  |  | 28000 | 0 | Funded by contributions | 28000 | 28000 | 0
| Runnymede Pleasure Ground | CMC - Sept 2017 | 4781000 |  |  | 4781000 | [6 empty] | 4781000
[9 empty] | 0 | 0 |  |  |  | 0
|  | Sub-totals | 5895647 | 39095 | 515406 | 4981000 | 203000 | 155000 | 1027501 | -4868146 |  |  |  | 0 | 75240 | 264389
Corporate & Business Services | [8 empty] | 0 |  |  |  |  | 0
Corporate Property | [8 empty] | 0 | 0 |  |  |  | 0
| Provision for Asset Management | - | 400000 |  | 100000 | 100000 | 100000 | 100000 | 400000 | 0 | Subject to individual Cttee reports | 420000 | 400000 | 20000 |  | 20000 | -20000
| 168 High Street Egham | CMC - Mar 2017 | 1638000 |  | 1638000 |  |  |  | 1638000 | 0 | £63k - SO42 Apr 2017 for Caffe Gondola Compensation
| Addlestone ONE Project | CMC - Sept 2014 | 75000000 | 54156301 | 19093171 | 1750528 |  |  | 75000000 | 0 |  | 75000000 | 75000000 | 0 | 24933346 | 37213834 | -12280488
| Marshall Place redevelopment | CMC - Jun 2016 | 2835000 |  | 2685000 | 150000 |  |  | 2835000 | 0 |  | 2835000 | 2835000 | 0 |  | 0
| 8 Station Road North | CMC - Mar 2017 | 143500 |  | 143500 |  |  |  | 143500 | 0
| Ashdene House redevelopment | CMC - Dec 2016 | 6000000 |  | 2000000 | 3700000 | 300000 |  | 6000000 | 0 |  | 6000000 | 6000000 | 0
| Development Loans | CMC - Nov 2014 | 26322571 | 1400000 | 24922571 |  |  |  | 26322571 | 0 |  | 26322571 | 26322571 | 0 | 1400000 | 1400000 | 0
| Loan - Virginia Water Scouts | CMC - May 2017 | 90000 |  | 90000 |  |  |  | 90000 | 0
RRP - Runnymede Regeneration Projects |  |  | 0 | [5 empty] | 0 | 0
| Egham Regeneration Gateway Phase 1 | Council - Nov 2016 | 89361740 |  | 42761740 | 37600000 | 4500000 | 4500000 | 89361740 | 0 |  | 90000000 | 89361740 | 638260
| - SCC Land purchase - Egham Regen Gateway Phase 1 | CMC - Mar 2017 | 191820 |  | 191820 |  |  |  | 191820 | 0
| - 7 Church Road, Egham | CMC - Mar 2017 | 446440 |  | 446440 |  |  |  | 446440 | 0
| Egham Leisure Centre Development | CMC - June 2017 | 19000000 |  | 9700000 | 7500000 | 900000 | 900000 | 19000000 | 0 | Additonal £1m approved CMC June 2017 | 18000000 | 19000000 | -1000000
Property Investment Strategy Purchases | [8 empty] | 0 | 0 |  | 0 | 0 | 0
| Prior year purchases / Future provision | CMC - Dec 2016 | 297877209 |  | 97877209 | 100000000 | 100000000 | 0 | 297877209 | 0 |  | 434086500 | 297877209 | 136209291 |  | 3898917 | -3898917
| Waitrose/Travelodge, Egham | CMC - Aug 2016 | 22960000 | 22912555 | 47445 |  |  |  | 22960000 | 0 |  | 22960000 | 22960000 | 0 | 22911610 | 22960000 | -48390
| Property Acquisition, Chertsey | CMC - Aug 2016 | 2657000 | 0 | 2657000 |  |  |  | 2657000 | 0 |  | 2657000 | 2657000 | 0 |  | 2657000 | -2657000
| Compass House, Chertsey - Car park remediation works | CMC - May 2017 | 170000 |  | 170000 |  |  |  | 170000 | 0 |  | 26548900 | 170000 | 26378900 | 26452743 | 26548900 | -96157
| 6 Station Road, Egham | SO42 - Nov 2016 | 580000 | 27500 | 552500 |  |  |  | 580000 | 0 |  | 580000 | 580000 | 0 |  | 33000 | -33000
| Egham Business Park | CMC - Dec 2016 | 32252000 | 1638554 | 30613446 |  |  |  | 32252000 | 0 |  | 32252000 | 32252000 | 0 | 1530360 | 1527500 | 2860
| 610 Chiswick High Road | CMC - Jan 2017 | 68502448 | 1333186 | 67169262 |  |  |  | 68502448 | 0 |  | 68502447 | 68502448 | -1 | 1302000 | 1302000 | 0
| Unither House, Chertsey | CMC - Jun 2017 | 7659000 |  | 7659000 |  |  |  | 7659000 | 0
ICT General Provisions |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0
| ICT Hardware Replacement | CMC - June 2017 | 153480 |  | 33480 | 40000 | 40000 | 40000 | 153480 | 0 | Annual provision available to draw down | 424077 | 153480 | 270597 | 20773 | 24077 | -3304
| ICT Upgrades & Developments | - | 475670 | 19640 | 156030 | 100000 | 100000 | 100000 | 475670 | 0 | Annual provision available to draw down | 450000 | 475670 | -25670 | 21010 | 50000 | -28990
ICT Specific Schemes |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0
| VDI - Virtual Desktop Infrastructure Solution | CMC - June 2017 | 173100 |  | 105600 | 22500 | 22500 | 22500 | 173100 | 0
| Customer Services Modernisation |  | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0
| - Customer Services Telephones | CMC - Dec 2016 | 15830 |  | 15830 |  |  |  | 15830 | 0 |  | 15830 | 15830 | 0 |  | 15830 | -15830
| - Capita Customer Relationship Management (CRM) | CMC - Jul 2017 |  |  | 75000 |  |  |  | 75000
| - Online Portal - E Billing | CMC - Jul 2017 |  |  | 45000 |  |  |  | 45000
| - Contingency/Connectors | CMC - Jul 2017 |  |  | 10000 |  |  |  | 10000
| - Hardware/Hosting Costs | CMC - Jul 2017 |  |  | 10000 |  |  |  | 10000
|  |  | 0 | [5 empty] | 0 | 0 |  |  |  | 0
|  | Sub-totals | 654904808 | 81487736 | 310969044 | 150963028 | 105940000 | 5640000 | 655044808 | 140000 |  |  |  | 0 | 78571842 | 97651058
0
0
Summary | [13 empty] | 0
| Housing Services |  | 18442499 | 102813 | 6002899 | 7073777 | 2251507 | 2251507 | 17682503 |  |  | 20055461 | 18442499 | 1612962
| Community Services |  | 5895647 | 39095 | 515406 | 4981000 | 203000 | 155000 | 1027501 |  |  | 1307820 | 5895647 | -4587827
| Environment & Sustainability |  | 2146620 | 294665.02 | 951955 | 300000 | 300000 | 300000 | 2146620.02 |  |  | 2129856 | 2146620 | -16764
| Corporate and Business Services |  | 654904808 | 81487736 | 310969044 | 150963028 | 105940000 | 5640000 | 655044808 |  |  | 819713677 | 654904808 | 164808869
[12 empty] | 0 |  | 0
|  | Total | 681389574 | 81924309.02 | 318439304 | 163317805 | 108694507 | 8346507 | 675901432.02 | -5488141.98
0
| Increase/(Reduction) in programme |  |  |  | 6073118 | 10432999 | -60000 | -60000 |  |  | Variation against approved Programme (January 2017)
Note on R15: Princess Christian: Deemed VFM; Chairman and VP indication to purchase property in Addlestone for propbably 12 flat development.
Note on R47: Princess Christian: 31/01/2017: Tender for a play area - Jo Harper Spend for 17/18. Tendering long process